## Sheet1
| Owner | Estimated Effort | ECS | Yes
Ramp-up On MicroServices & DynamoDB | LetsDoc | 5 days | DynamoDB | No
Data Model - Refer the Access Health Docs | All Teams | 5 days | Aurora | Yes
MicroServices Design (Application Level Design) | All Teams | 10 days | DevOps | Yes
Release Plan | LetsDoc | 2 days | API Gateway | Yes
Update Acceptence Criteria | LetsDoc & Access health | 3 Weeks | SQS | No
Infrastructure/Solution Architecture | AWS & LetsDoc | 5 days | Redis | Yes
AWS account setup | AWS & LetsDoc
Setup JIRA/Project Management Tool | Access Health